## Sheet1
Date | Duration (h) | Timeframe | Topic | Status | PIC | ADO
2025-01-09 | 8 | 08:00-17:30 | Mock Project - Day 1 - Kick off + Create requirement outline | Finished | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-01-14 | 8 | 08:00-17:30 | Mock Project - Day 2 - Create SRS | Finished | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-01-16 | 8 | 08:00-17:30 | Mock Project - Day 3 - Review and update SRS | Finished | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-01-21 | 8 | 08:00-17:30 | Mock Project - Day 4 - Review and update SRS | Finished | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-02-06 | 8 | 08:00-17:30 | Mock Project - Day 5 - Database Design | Finished | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-02-11 | 8 | 08:00-17:30 | Mock Project - Day 6 - Review Database Design | Finished | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-02-13 | 8 | 08:00-17:30 | Mock Project - Day 7 - Create Blackbox Testcase | Finished | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-02-18 | 8 | 08:00-17:30 | Mock Project - Day 8 - Review and update Blackbox TC | Finished | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-02-20 |  | 08:00-17:30 | Mock Project - Day 9 - Coding-Front end | Starting | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-02-26 |  | 08:00-17:30 | Mock Project - Day 10 - Coding module 1 | Starting | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-03-02 |  | 08:00-17:30 | Mock Project - Day 11 - Coding module 2 |  | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-03-08 |  | 08:00-17:30 | Mock Project - Day 12 - Coding module 3 |  | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-03-14 |  | 08:00-17:30 | Mock Project - Day 17 - Review code + UT |  | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-03-16 | 2 | 08:00-10:00 | Mock Project - Day 18 - IT + Create Test Report |  | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-03-22 | 2 | 12:30-14:45 | Mock Project - Day 19 - Final Report |  | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
2025-03-24 | 2 | 15:00-17:15 | Mock Project - Day 20 - Final Report (cont) |  | AnNNH,PhuongPH,MinhDQ | AnNNH,PhuongPH,MinhDQ
Tên đề tài: | Xây dựng website quản lý câu lạc bộ
Nguyễn Nghĩa Hải An
Phan Hoàng Phương
Đặng Quang Minh