## Sheet1
Date | Duration (h) | Timeframe | Topic | Status
2025-01-09 | 8 | 08:00-17:30 | Mock Project - Day 1 - Kick off + Create requirement outline | Finished
2025-01-14 | 8 | 08:00-17:30 | Mock Project - Day 2 - Create SRS | Finished
2025-01-16 | 8 | 08:00-17:30 | Mock Project - Day 3 - Review and update SRS | Finished
2025-01-21 | 8 | 08:00-17:30 | Mock Project - Day 4 - Review and update SRS | Finished
2025-02-06 | 8 | 08:00-17:30 | Mock Project - Day 5 - Database Design | Finished
2025-02-11 | 8 | 08:00-17:30 | Mock Project - Day 6 - Review Database Design | Started
2025-02-13 | 8 | 08:00-17:30 | Mock Project - Day 7 - Create Blackbox Testcase
2025-02-18 | 8 | 08:00-17:30 | Mock Project - Day 8 - Review and update Blackbox TC
2025-02-20 | 8 | 08:00-17:30 | Mock Project - Day 9 - Coding
2025-02-25 | 8 | 08:00-17:30 | Mock Project - Day 10 - Coding
2025-02-27 | 8 | 08:00-17:30 | Mock Project - Day 11 - Coding
2025-03-04 | 8 | 08:00-17:30 | Mock Project - Day 12 - Coding
2025-03-06 | 8 | 08:00-17:30 | Mock Project - Day 13 - Coding
2025-03-03 | 8 | 08:00-17:30 | Mock Project - Day 14 - Coding
2025-03-11 | 8 | 08:00-17:30 | Mock Project - Day 15 - Coding
2025-03-20 | 8 | 08:00-17:30 | Mock Project - Day 16 - Coding
2025-03-21 | 8 | 08:00-17:30 | Mock Project - Day 17 - Review code + UT
2025-03-28 | 2 | 08:00-10:00 | Mock Project - Day 18 - IT + Create Test Report
2025-04-01 | 2 | 12:30-14:45 | Mock Project - Day 19 - Final Report
2025-04-03 | 2 | 15:00-17:15 | Mock Project - Day 20 - Final Report (cont)
Tên đề tài: | Xây dựng website quản lý câu lạc bộ
Nguyễn Nghĩa Hải An
Phan Hoàng Phương
Đặng Quang Minh